## WBS
Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2026-10-13
Project Team Name |  | Nguyễn Tú Anh (cá nhân)
Project Topic |  | LangGraph Research Assistant Agent
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
1. Design |  |  | 2026-10-13 |  |  |  | Done | bar: 2021-11-01 to 2021-11-13
1.1. Research | bar: 2021-11-01 to 2021-11-13
| 1.2. Design Architecture | [5 empty] | Done | bar: 2021-11-01 to 2021-11-12
| 1.3. Design State & Workflow | [5 empty] | Done | bar: 2021-11-01 to 2021-11-08
1.4. Complete actions plans and WBS | bar: 2021-11-01 to 2021-11-08
2. Implementation | [6 empty] | Done | bar: 2021-11-01 to 2021-11-06
| 2.1. Setup Python, uv, API environment | [5 empty] | Done
| 2.2 Implement analyst structured models | [5 empty] | Done
| 2.3 Implement analyst generation graph | [5 empty] | Done
| 2.4. Implement human feedback interupt | [5 empty] | Done
| 2.5. Implement parallel fan in/out | [5 empty] | Done
| 2.6. Implement report synthesis | [5 empty] | Done
3. Testing and evaluation | [6 empty] | Done
| 3.1. Unit test nodes, edges, schemas | [5 empty] | Done
| 3.2 Integration and workflow test | [5 empty] | Done
| 3.3. Evalute grounding and ciations | [5 empty] | Done
| 3.4. Performance, cost and error handling | [5 empty] | Done
4. Documentation and delivery | [6 empty] | Done
| 4.1. Write final report | [5 empty] | Done
| 4.2. Prepare demo | [5 empty] | Done
| 4.3. Final review and submition | [5 empty] | Done